## Issue Log
Date Reported | Issue Description | Priority | Assigned To | Status | Resolution
1 | SIQ need to be updated according to readablity. | high | Aya Mostafa (PM) | Closed | fine tuned siq document and resended to customer to confirmed
2 | Release strategy not created. | medium | Sohila Abdalla | Closed
3 | Branch strategy not created. | low | Sohila Abdalla | Closed
4 | SRS is not detailed as needed. | high | team | Closed
5 | internal change management not mentioned well in PM. | medium | Sara Hassan | Closed
6 | Sondos is absent | medium | whole members | Closed | delay in delivery due to increase in work
7 | Integration errors | high | whole members | Opend
8
9
10