## TimePlan
Phase | Task Name | Description | Owner | reviewer | Start Date | Due Date | Estimated Time | Actual Time | Status
Planing | REQ_SIQ | reorganize the list of features to be more clear to understand | Aya | Sohaila | 20/4 | 23/4 | 1 | 1 | closed
| REQ_SRS | reorganize the list of features to be more clear to understand | Aya | Sohaila | 20/4 | 23/4 | 1 | 1 | closed
| REQ_RTM | update the RTM depending on the SIQ &SRS changes | Aya | Mayar | 20/4 | 23/4 | 1 | 1 | closed
| PMP_Plan_BackLog | making time plan for new phase | Aya | Aya | 20/4 | 20/4 | 2 | 2 | closed
Design | DES_Understanding | face to face meeting to understand the designs and what will ever one do | Whole team, couches and the quality manager |  | 20/4 | 20/4 | 3 hours for every member | 3 | closed
| DES_HL_UseCase | high level design using use case digram | Mayar | Aya | 20/4 | 23/4 | 4 | 4 | closed
| DES_HL_Decomposition | high level design using decomposition diagram | Sondos | Mayar | 20/4 | 21/4 | 2 | 2 | closed
| DES_HL_ERD | high level design using ERD for database | Sara | Sohaila | 20/4 | 23/4 | 4 | 3 | closed
| DES_LL_WireframUI | low level design for system UI screens | Sondos | Aya | 20/4 | 23/4 | 3 | 3 | closed
| DES_LL_ClassDiagram | low level design for every feature and its releated functions using class diagram | Dina | Sohaila | 20/4 | 24/4 | 4 | 4 | closed
| DES_LL_FlowChart | low level design for all features in the system using flow charts | Sohaila | Dina | 20/4 | 24/4 | 5 | 5 | closed
| Fixing DES_HL_Decomposition | account and user transaction to be added | Sara | Aya | 27/4 | 28/4 | 1 | 1 | closed
| Fixing DES_LL_ClassDiagram | need to include validation functions | Sohaila | Dina | 27/4 | 28/4 | 2 | 4 | inprogress
| Fixing DES_LL_FlowChart | need to be more detailed | Dina | Sohaila | 27/4 | 28/4 | 1 | 2 | closed
| Fixing DES_HL_ERD | Admin entity need to be deleted | Aya | Aya | 27/4 | 28/4 | 1 | 1 | closed
| DEV_Understanding | face to face meeting to understand the designs and what will ever one do | Whole team, couches and the quality manager |  | 27/4 | 27/4 | 3 hours for every member | 3 | closed
Development | DEV_Front_Registration | Implement the frontend for Registration page | Sara | Dina | 3/5 | 9/5 | 7 | 8 | closed
| DEV_Front_Login | Implement the frontend for Login page | Sara | Dina | 3/5 | 9/5 | 4 | 5 | closed
| DEV_Front_UserTransaction | Implement the frontend forUser Transaction page | Dina | Sara | 3/5 | 9/5 | 5 | 6 | closed
| DEV_Front_Admin | Implement the frontend for Admin page | Dina | Sara | 3/5 | 9/5 | 7 | 9 | closed
| DEV_Back_Registration | Implement the backend for Registration page | Aya | Aya | 3/5 | 9/5 | 5 | 5 | closed
| DEV_Back_Login | Implement the backend for Login page | Aya | Mayar | 3/5 | 9/5 | 3 | 4 | closed
| DEV_Back_UserTransaction | Implement the backend forUser Transaction page | Mayar | Sohaila | 3/5 | 9/5 | 7 | 8 | closed
| DEV_Back_Admin | Implement the backend for Admin page | Sohaila | Mayar | 3/5 | 9/5 | 9 | 9 | closed
| DEV_Back_Database | Make Database for the system | Mayar | Aya | 3/5 | 9/5 | 4 | 4 | closed
| DEV_Plan_BackLog | making time plan for the Design phase | Aya | Aya | 3/5 | 3/5 | 3 | 3 | closed

## Effort Estimation
Name | Effort Capacity | Effort Planned
Aya | 15 | 17
Sohaila | 15 | 18
Mayar | 10 | 11
Sara | 15 | 17
Sondos | 5 | 5
Dina | 15 | 18