## Time Plan
Phase | Task Name | Description | Owner | reviewer | Start Date | Due Date | Estimated Time | Actual Time | Status
Planing | REQ_SIQ | reorganize the list of features to be more clear to understand | Aya | Sohaila | 20/4 | 23/4 | 1 | 1 | closed
| REQ_SRS | reorganize the list of features to be more clear to understand | Aya | Sohaila | 20/4 | 23/4 | 1 | 1 | closed
| REQ_RTM | update the RTM depending on the SIQ &SRS changes | Aya | Mayar | 20/4 | 23/4 | 1 | 1 | closed
| PMP_Plan_BackLog | making time plan for new phase | Aya | Aya | 20/4 | 20/4 | 2 | 2 | closed
Design | DES_Understanding | face to face meeting to understand the designs and what will ever one do | Whole team, couches and the quality manager |  | 20/4 | 20/4 | 3 hours for every member | 3 hours for every member | closed
| DES_HL_UseCase | high level design using use case digram | Mayar | Aya | 20/4 | 23/4 | 4 | 4 | closed
| DES_HL_Decomposition | high level design using decomposition diagram | Sondos | Mayar | 20/4 | 21/4 | 2 | 2 | closed
| DES_HL_ERD | high level design using ERD for database | Sara | Sohaila | 20/4 | 23/4 | 4 | 3 | closed
| DES_LL_WireframUI | low level design for system UI screens | Sondos | Aya | 20/4 | 23/4 | 3 | 3 | closed
| DES_LL_ClassDiagram | low level design for every feature and its releated functions using class diagram | Dina | Sohaila | 20/4 | 24/4 | 4 | 4 | closed
| DES_LL_FlowChart | low level design for all features in the system using flow charts | Sohaila | Dina | 20/4 | 24/4 | 5 | 5 | closed

## Effort Estimation
Name | Effort Capacity | Effort Planned
Aya | 10 | 8
Sohaila | 10 | 8
Mayar | 10 | 7
Sara | 10 | 7
Sondos | 10 | 8
Dina | 10 | 7