## coaching Review
Number | Comments | Date | Reviewer | Status | Release version
1 | revision record should be added to PMP | 29/3/2024 | Esraa | closed | V1.0
2 | release strategy should be added to PMP | 29/3/2024 | Esraa | closed | V1.0
3 | baseline strategy should be added to PMP | 29/3/2024 | Esraa | open | V1.0
4 | tuesdays meetings should be added to PMP | 30/3/2024 | Mohammed Hassan | closed | V1.0
5 | page 4 issues tracking record should be added to PMP | 30/3/2024 | Mohammed Hassan | closed | V1.0
6 | esclation process should be added to PMP | 30/3/2024 | Mohammed Hassan | closed | V1.0
7 | update folder structure in CIL | 30/3/2024 | Mohammed Hassan | closed | V1.0
8 | internal change request should be mentioned in PMP | 30/3/2024 | Mohammed Hassan | open | V1.0
9 | commit message need to be clear | 30/3/2024 | Mohammed Hassan | closed | V1.0
10 | add review phase between inprogress and finish in trello | 30/3/2024 | Mohammed Hassan | closed | V1.0
11 | release name doesn't follow the release naming convension as mensioned in PMP | 17/4/2024 | Esraa | closed | V2.0
12 | in [Req_SIQ]: the second tab should be named "Revision Record" not Report. | 17/4/2024 | Esraa | closed | V2.0
13 | Why is there REQ_SIQ and REQ_SIQ_Responses not only one sheet? | 17/4/2024 | Esraa | closed | V2.0
14 | account/user deletion criteria must be mentioned | 20/4/2024 | Mohammed Hassan | closed | V3.0
15 | the footer part of theDES_LL_WireframeUI | 25/4/2024 | Esraa | closed | V3.0
16 | the DES_HL_Decomposition missing account and user transaction | 27/4 | AMR | onprogress | V4.0
17 | DES_LL_FlowChart should be more detaild | 27/4 | AMR | onprogress | V4.0
18 | DES_LL_ClassDiagram need to include validation functions | 27/4 | AMR | onprogress | V4.0
19 | DES_HL_ERD the Admin entity need to be deleted | 27/4 | AMR | onprogress | V4.0