## الورقة1
Release version | ID | Comments | Date | Reviewer | Status
V1 | 1 | revision record should be added to PMP | 2024-03-29 | Esraa | closed
V1 | 2 | release strategy should be added to PMP | 2024-03-29 | Esraa | closed
V1 | 3 | baseline strategy should be added to PMP | 2024-03-29 | Esraa | open
V1 | 4 | tuesdays meetings should be added to pmp | 2024-03-30 | Mohammed Hassan | open
V1 | 5 | page 4 issues tracking record should be added to PMP | 2024-03-30 | Mohammed Hassan | open
V1 | 6 | esclation process should be added to PMP | 2024-03-30 | Mohammed Hassan | open
V1 | 7 | update folder structure in CIL | 2024-03-30 | Mohammed Hassan | open
V1 | 8 | internal change request should be mentioned in PMP | 2024-03-30 | Mohammed Hassan | open
V1 | 9 | commit message need to be clear | 2024-03-30 | Mohammed Hassan | closed
V1 | 10 | add review phase between inprogress and finish in trello | 2024-03-30 | Mohammed Hassan | closed