## الورقة1
Number | Comments | Date | Reviewer | Status | Release version
1 | revision record should be added to PMP | 29/3/2024 | Esraa | closed | V1
2 | release strategy should be added to PMP | 29/3/2024 | Esraa | closed | V1
3 | baseline strategy should be added to PMP | 29/3/2024 | Esraa | open | V1
4 | tuesdays meetings should be added to PMP | 30/3/2024 | Mohammed Hassan | closed | V1
5 | page 4 issues tracking record should be added to PMP | 30/3/2024 | Mohammed Hassan | closed | V1
6 | esclation process should be added to PMP | 30/3/2024 | Mohammed Hassan | closed | V1
7 | update folder structure in CIL | 30/3/2024 | Mohammed Hassan | closed | V1
8 | internal change request should be mentioned in PMP | 30/3/2024 | Mohammed Hassan | open | V1
9 | commit message need to be clear | 30/3/2024 | Mohammed Hassan | closed | V1
10 | add review phase between inprogress and finish in trello | 30/3/2024 | Mohammed Hassan | closed | V1