## Time Plan
Phase | Task Name | Description | Owner | reviewer | Start Date | Due Date | Estimated Time | Actual Time | Status
Planing | REQ_SIQ | reorganize the list of features to be more clear to understand | Aya | Sohaila | 20/4 | 23/4 | 2 | 2 | opened
| REQ_SRS | reorganize the list of features to be more clear to understand | Aya | Sohaila | 20/4 | 23/4 | 2 | 2 | opened
| REQ_RTM | update the RTM depending on the SIQ &SRS changes | Aya | Mayar | 20/4 | 23/4 | 2 |  | opened
| PMP_Plan_BackLog | making time plan for new phase | Aya | Aya | 20/4 | 20/4 | 3 | 3 | closed
Design | DES_HL_UseCase | high level design using use case digram | Mayar | Aya | 20/4 | 23/4 | 7 |  | opened
| DES_HL_Decomposition | high level design using decomposition diagram | Sondos | Mayar | 20/4 | 21/4 | 3 |  | closed
| DES_HL_ERD | high level design using ERD for database | Sara | Aya | 20/4 | 23/4 | 7 |  | opened
| DES_LL_WireframUI | low level design for system UI screens | Sondos | Aya | 20/4 | 23/4 | 3 |  | opened
| DES_LL_ClassDiagram | low level design for every feature and its releated functions using class diagram | Dina | Sohaila | 20/4 | 24/4 | 8 |  | opened
| DES_LL_FlowChart | low level design for all features in the system using flow charts | Sohaila | Dina | 20/4 | 24/4 | 9 |  | opened

## Effort Estimation
Name | Effort Capacity
Aya | 6
Sohaila | 6
Mayar | 6
Sara | 6
Sondos | 6
Dina | 6