## Issue Log
Date Reported | Issue Description | Priority | Assigned To | Status | Resolution
1 | SIQ need to be updated according to readablity. | high | Aya Mostafa (PM) | Closed | fine tuned siq document and resended to customer to confirmed
2 | Release strategy not created. | medium | Sohila Abdalla
3 | Branch strategy not created. |  | Sohila Abdalla
4 | SRS is not detailed as needed. |  | team
5 | internal change management not mentioned well in PM. |  | Sara Hassan
6
7
8
9
10